## main
#story | story_title | story description | story_estimation/ range out of 10 | HC&HV | LC&HV | HC&LV | LC&LV | User_role | Pre-Requirements | QATest | Responsible person in a team | Iteration | Deadline
1 | Chat-Program Info | As an applicant, I want to ask the chatbot questions about educational programs, so that I can quickly get information about available programs | 4 |  | yes |  |  | Applicant | Access to the programs database | US1QATest | Arman | 1 | 20 Sep 2026
3 | Admission Requirements FAQ | As an applicant, I want to ask questions about admission requirements, so that I know what conditions I need to meet | 3 |  | yes |  |  | Applicant | Up-to-date database of requirements per program | US3QATest | Saken | 1 | 27 Sep 2026
5 | Admission FAQ | As an applicant, I want to get answers to frequently asked admission questions, so that I don't have to search for information manually | 2 |  | yes |  |  | Applicant | FAQ database maintained by staff | US5QATest | Arman | 1 | 27 Sep 2026
4 | Required Documents Info | As an applicant, I want to receive information about required documents, so that I can prepare a complete document package | 3 |  | yes |  |  | Applicant | List of documents per program | US4QATest | Shadiyar | 2 | 11 Oct 2026
15 | Account Registration & Verification | As an applicant, I want to register an account using my email or phone number and verify it via a 6-digit code (Email, SMS, or Telegram Bot), so that my data is securely stored and authenticated. | 6 |  | yes |  |  | Applicant | Database user model and notification gateways (SMTP, Telegram bot, SMS) | US15QATest | Arman | 2 | 11 Oct 2026
16 | Applicant Profile & Saved Programs | As an applicant, I want to create a personal profile with my target degree and bookmark preferred programs, so that I can easily track my favorite educational choices. | 4 |  | yes |  | yes | Applicant | Authenticated user session; programs database | US16QATest | Saken | 2 | 11 Oct 2026
17 | Secure Password Recovery | As an applicant, I want to reset my password using a secure 6-digit code delivered via email or Telegram bot, so that I can regain access if I forget my password. | 4 |  | yes |  |  | Applicant | User authentication system; Email SMTP and Telegram bot services | US17QATest | Yertai | 2 | 11 Oct 2026
7 | Step-by-Step Admission Guide | As an applicant, I want to receive a step-by-step guide to the admission procedure, so that I understand what actions I need to take | 5 |  | yes |  |  | Applicant | Up-to-date admissions office regulations | US7QATest | Saken | 3 | 18 Oct 2026
9 | Official Source Links | As an applicant, I want to receive links to official university sources, so that I can independently verify information | 2 |  |  |  | yes | Applicant | Database of links to official pages | US9QATest | Arman | 3 | 25 Oct 2026
18 | UNT Eligibility Matcher | As an applicant, I want to enter my UNT profile subjects and scores, so that the assistant can instantly show which programs I am qualified to apply for. | 5 | yes | yes |  |  | Applicant | Program requirements database with UNT threshold scores and subject pairs | US18QATest | Shadiyar | 3 | 25 Oct 2026
19 | Tuition & Grant Calculator | As an applicant, I want to calculate estimated annual tuition fees and my probability of winning a state or university grant, so that I can plan my higher education budget. | 5 | yes | yes |  |  | Applicant | Tuition fee structure and historical grant passing score thresholds | US19QATest | Yertai | 3 | 25 Oct 2026
8 | Deadline Notifications | As an applicant, I want to receive information about document submission deadlines, so that I don't miss important dates | 4 |  | yes |  |  | Applicant | Admissions campaign deadline calendar | US8QATest | Shadiyar | 4 | 1 Nov 2026
13 | Manage FAQ Database | As a university staff member, I want to manage the FAQ knowledge base, so that the chatbot provides accurate answers to common applicant questions. |  | yes | yes |  |  | University Staff | Staff authentication/role system in place; FAQ storage structure defined | US13QATest | Arman | 4 | 8 Nov 2026
20 | Telegram Push Alerts | As an applicant, I want to receive automated push alerts in Telegram 3 days and 1 day before application deadlines, so that I never miss submission cutoffs. | 4 |  | yes |  |  | Applicant | Telegram bot integration linked to applicant accounts; deadline calendar | US20QATest | Saken | 4 | 8 Nov 2026
21 | Document Pre-check Validator | As an applicant, I want to check my document readiness against a real-time checklist and upload test scans to verify format compliance (PDF/JPEG), so that my application is not rejected. | 5 |  | yes |  |  | Applicant | Required documents database; file validation service | US21QATest | Yertai | 4 | 8 Nov 2026
6 | Application Status Check | As an applicant, I want to check my application status through the assistant, so that I know what stage my application is at | 6 |  | yes |  | yes | Applicant | Integration with the admissions office system (application statuses) | US6QATest | Saken | 5 | 15 Nov 2026
10 | Admission Info Update | As a university staff member, I want to update the admission information used by the assistant, so that applicants receive accurate data | 6 | yes | yes |  |  | University Staff | Admin panel / editing access to the database | US10QATest | Shadiyar | 5 | 22 Nov 2026
22 | Online Application Submission | As an applicant, I want to submit a preliminary admission application with my contact details and chosen specialty online, so that the university admissions committee can review it immediately. | 6 | yes | yes |  |  | Applicant | Applicant account system; application processing database table | US22QATest | Arman | 5 | 22 Nov 2026
23 | Staff Application Review Portal | As an admissions manager, I want to view incoming applications, change review statuses (Pending, Approved, Requires Correction), and add staff comments, so that applicants are kept informed. | 6 | yes | yes |  |  | University Staff | Admin/manager RBAC permissions; application workflow engine | US23QATest | Yertai | 5 | 22 Nov 2026
2 | Program Recommendation | As an applicant, I want to receive program recommendations based on my interests and goals, so that I can choose a suitable program | 8 | yes | yes |  |  | Applicant | AI recommendation model integration + programs database | US2QATest | Yertai | 6 | 29 Nov 2026
12 | Program Comparison | As an applicant, I want to compare several programs by criteria (cost, grants, passing score), so that I can make an informed decision. | 5 |  | yes |  |  | Applicant | Program catalog with comparable attributes (cost, grants, passing score) available | US12QATest | Yertai | 6 | 6 Dec 2026
24 | Career Pathways Advisor | As an applicant, I want to see typical career roles, average starting salaries, and partner hiring companies for each program, so that I can choose a major with clear career prospects. | 5 | yes | yes |  |  | Applicant | Programs database expanded with career outcomes and employment data | US24QATest | Saken | 6 | 6 Dec 2026
25 | Excel Report Export for Admissions | As an admissions manager, I want to export applicant registrations, inquiries, and popular program statistics into Excel spreadsheets (.xlsx), so that the admissions department can prepare official recruitment reports. | 4 | yes | yes |  |  | University Staff | openpyxl library integrated; reporting database queries | US25QATest | Arman | 6 | 6 Dec 2026
11 | Multilingual Support | As an applicant, I want to interact with the assistant in Kazakh, Russian, or English, so that I can receive information in the language I'm most comfortable with. | 5 | yes | yes |  |  | Applicant | NLP/translation engine integrated; content available in all 3 languages | US11QATest | Saken | 7 | 13 Dec 2026
14 | Escalation Notification | As an applicant, I want to be notified when the assistant cannot confidently answer my question, so that I can contact the appropriate university department. | 4 |  | yes |  |  | Applicant | Confidence-scoring logic in chatbot; admissions department contact routing defined | US14QATest | Yertai | 7 | 20 Dec 2026
26 | Live Admissions Officer Chat Handoff | As an applicant, when the automated assistant cannot answer my complex personal question, I want to be transferred to a live admissions officer, so that I can receive real-time human assistance. | 7 | yes |  |  |  | Applicant | Chat session management; live message polling or WebSocket support | US26QATest | Arman | 7 | 20 Dec 2026
27 | Assistant Feedback & Quality Rating | As an applicant, I want to submit a 1-to-5 star rating and optional comments on the assistant's answer quality, so that the university can monitor satisfaction and improve the chatbot. | 3 |  | yes |  |  | Applicant | Feedback database table; chat session completion trigger | US27QATest | Shadiyar | 7 | 20 Dec 2026
Remarks: | HC&HV | High Cost &High Value | Do Later
| LC&HV | Low Cost & High Value | Do Now
| HC&LV | High Cost & Low Value | Never Do
| LC&LV | Low Cost & Low Value | Do much Later
Example
#story | story_title | story description | story_estimation/ range out of 10 | HC&HV | LC&HV | HC&LV | LC&LV | User_role | Pre-Requirements | QATest | Responsible Person in a team | Iteration/Sprint | deadline
1 | Track Flex Status | As an employee I want to be able to see my own flex-status and check that it has been computed correctly | 3 |  | yes |  |  | Employee | Employee must login to the system | UserStory1QAT | Askar Askarov, developer&designer | 1 | 22.02.2023
Note on D2: ====== ID#AAACGut5x24 Aliya Zhunis (2026-09-07 07:43:22) 10

## User Story1
|  | ⬅️ Back to Main Schedule | ➡️ View QA Test (US1QATest)
"User Story" | Stakeholders:
Program Info Chatbot Query :As an applicant, I want to ask the chatbot questions about educational programs, so that I can quickly get information about available programs. | Applicant, Admissions Office
responsibilities
The chatbot must recognize program-related questions (specialty, duration, cost, format) and return an accurate, up-to-date answer.
A user must be warned if the chatbot cannot confidently answer the question, and be offered a way to reach admissions staff.
A user must be warned if the chatbot cannot confidently answer the question, and be offered a way to reach admissions staff.
constraints
The chatbot must use the official, current program database/knowledge base — no outdated or unofficial sources.
Answers must be available in Kazakh, Russian, and English.
tags
Volatility = Medium
test scripts
System: (Pass) Five (5) different program-related questions are answered correctly and clearly.
System: (Fail) No answer is returned for a valid program question.
System: (Fail) Incorrect or outdated program information is returned.
System: (Deferred) Answer is returned with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured knowledge base of program information (specialty, cost, duration, format) for the chatbot to query.
Task (New): Create a fallback mechanism that flags unanswered/low-confidence questions and routes them to admissions staff.
Task (Verified): Set up periodic sync between the chatbot's knowledge base and the university's official program data source.

## US1QATest
The Given/When/Then Acceptance Criteria — Story 1 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story1)
User story:Chat-Program Info | As an applicant, I want to ask the chatbot questions about educational programs, so that I can quickly get information about available programs.
Scenario 1 | Successful program query
Given | The user opens the chatbot | Scenario-oriented acceptance criteria
When | The user asks a question about a specific program (e.g., cost, duration) | The Given/When/Then Acceptance Criteria Example 1
Then | The system returns the correct information about that program | User story: | As a user, I want to be able to recover the password to my account, so that I will be able to access my account in case I forgot the password
|  | Scenario 1 | Forgot password
Scenario 2 | Chatbot cannot answer confidently | Given | The user navigates to the login page
Given | The user asks a question outside the chatbot's knowledge base | When | The user selects <forgot password> option
When | The chatbot cannot find a confident answer | And | Enters a valid email to receive a link for password recovery
Then | The system informs the user it cannot answer | Then | The system sends the link to the entered email
And | The system offers to connect the user with admissions staff
|  | Scenario 2 | Recover password
|  | Given | The user receives the link via the email
|  | When | The user navigates through the link received in the email
|  | Then | The system enables the user to set a new password
The Given/When/Then Acceptance Criteria Example 2.1
|  | User story: | As a user, I want to be able to request the cash from my account at an ATM so that I will be able to receive the money from my account quickly and in different places
|  | Scenario 1 | Requesting the cash from a creditworthy account
|  | Given | that the account is creditworthy
|  | And | the card is valid
|  | And | the dispenser contains cash
|  | When | the customer requests the cash
|  | Then | ensure the account is debited
|  | And | ensure cash is dispensed
|  | And | ensure the card is returned
The Given/When/Then Acceptance Criteria Example 2.2
|  | User story: | As a user, I want to be able to request the cash from my account at an ATM so that I will be able to receive the money from my account quickly and in different places
|  | Scenario 2 | Requesting the cash from an overdrawn account
|  | Given | that the account is overdrawn
|  | And | the card is valid
|  | When | the customer requests the cash
|  | Then | ensure the rejection message is displayed
|  | And | ensure cash isn’t dispensed
Rule-oriented acceptance criteria format
Example
|  | User story: | As a user, I want to use a search field to type a city, name, or street, so that I could find matching hotel options.
Basic search interface acceptance criteria
The search field is placed on the top bar
Search starts once the user clicks “Search”
The field contains a placeholder with a grey-colored text: “Where are you going?”
The placeholder disappears once the user starts typing
Search is performed if a user types in a city, hotel name, street, or all combined
Search is in Kazakh, English, Russian, and German
The user can’t type more than 200 symbols
The search doesn’t support special symbols (characters). If the user has typed a special symbol, show the warning message: “Search input cannot contain special symbols.”
System Behavior
Strong Password Acceptance Criteria

## User Story 2
User Story 2 | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US2QATest)
Program Recommendation :As an applicant, I want to receive program recommendations based on my interests and academic goals, so that I can choose a suitable program. | Applicant, Admissions Office
responsibilities
The system must collect the applicant's interests, academic background, and goals (via a short questionnaire or chat dialogue).
The system must generate a ranked list of matching programs based on the applicant's input.
A user must be warned if not enough information was provided to generate a reliable recommendation.
constraints
Recommendations must be based only on currently offered, official university programs.
The recommendation logic must be able to update automatically when the program catalog changes.
tags
Volatility = Medium
test scripts
System: (Pass) A ranked list of relevant programs is generated for five (5) different applicant profiles.
System: (Fail) No recommendation is generated for a valid applicant profile.
System: (Fail) A recommended program is outdated or no longer offered.
System: (Deferred) Recommendations are generated with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a questionnaire/dialogue flow to capture applicant interests and academic goals.
Task (New): Create a matching/ranking algorithm linking applicant profiles to the program catalog.
Task (Verified): Set up a sync process so the recommendation engine reflects the current program catalog.

## US2QATest
The Given/When/Then Acceptance Criteria — Story 2 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 2)
User story: Program Recommendation | As an applicant, I want to receive program recommendations based on my interests and academic goals, so that I can choose a suitable program.
Scenario 1 | Successful recommendation
Given | The user provides their interests and academic goals
When | The user requests program recommendations
Then | The system returns a ranked list of matching programs
Scenario 2 | Insufficient information provided
Given | The user has not provided enough information about their interests or goals
When | The user requests program recommendations
Then | The system warns the user that more information is needed
And | The system prompts the user to provide additional details

## User Story 3
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US3QATest)
Admission Requirements Query :As an applicant, I want to ask questions about admission requirements, so that I know which conditions I need to meet. | Applicant, Admissions Office
responsibilities
The chatbot must recognize questions about admission requirements (exam scores, prerequisites, language proficiency, etc.) and return accurate, program-specific answers.
A user must be warned if the requirements for their chosen program are not yet available or are still under review.
The chatbot must distinguish between requirements for different applicant categories (e.g., local vs. international, undergraduate vs. graduate).
constraints
The chatbot must use the official, current admission requirements — no outdated or unofficial sources.
Answers must be available in Kazakh, Russian, and English.
tags
Volatility = Medium
test scripts
System: (Pass) Five (5) different requirement-related questions are answered correctly for different programs/categories.
System: (Fail) No answer is returned for a valid requirements question.
System: (Fail) Outdated or incorrect requirements are returned.
System: (Deferred) Answer is returned with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured database of admission requirements per program and applicant category.
Task (New): Create logic to disambiguate applicant category when a question is ambiguous.
Task (Verified): Set up periodic sync between the chatbot's requirements data and the official admissions policy source.

## US3QATest
The Given/When/Then Acceptance Criteria — Story 3 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 3)
User story: Admission Requirements Query | As an applicant, I want to ask questions about admission requirements, so that I know which conditions I need to meet.
Scenario 1 | Successful requirements query
Given | The user opens the chatbot
When | The user asks about admission requirements for a specific program
Then | The system returns the correct requirements for that program
Scenario 2 | Requirements not yet available
Given | The user asks about requirements for a program that is under review
When | The chatbot checks the requirements database
Then | The system informs the user the requirements are not yet finalized
And | The system offers to notify the user once they are available

## User Story 4
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US4QATest)
Required Documents Info :As an applicant, I want to receive information about the necessary documents, so that I can prepare a complete application package. | Applicant, Admissions Office
responsibilities
The chatbot must provide a complete, program-specific list of required documents (e.g., diploma, ID, test scores, photos).
A user must be warned if a document requirement depends on their applicant category (e.g., local vs. international) and prompted to clarify if needed.
The chatbot must indicate the accepted format for each document (original, notarized copy, scan, etc.).
constraints
The document list must reflect the official, currently approved admissions checklist — no outdated items.
Answers must be available in Kazakh, Russian, and English.
tags
Volatility = Medium
test scripts
System: (Pass) The full, correct document checklist is returned for five (5) different program/category combinations.
System: (Fail) A required document is missing from the returned list.
System: (Fail) An outdated or no-longer-required document is included in the list.
System: (Deferred) The document list is returned with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured database of required documents per program and applicant category.
Task (New): Create logic to clarify applicant category when it affects the document list.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US4QATest
The Given/When/Then Acceptance Criteria — Story 4 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 4)
User story: Required Documents Info | As an applicant, I want to receive information about the necessary documents, so that I can prepare a complete application package.
Scenario 1 | Successful document checklist query
Given | The user opens the chatbot
When | The user asks what documents are needed for a specific program
Then | The system returns the complete, correct list of required documents
Scenario 2 | Applicant category unclear
Given | The user's applicant category (e.g., local or international) is not specified
When | The user asks what documents are needed
Then | The system asks the user to clarify their applicant category
And | The system returns the correct document list once clarified

## User Story 5
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US5QATest)
Admission FAQ :As an applicant, I want to receive answers to frequently asked questions about admission, so that I don't have to search for information manually on the university website. | Applicant, Admissions Office
responsibilities
The chatbot must retrieve accurate answers from a maintained FAQ knowledge base for common admission questions.
A user must be warned if their question is not covered in the FAQ and be offered a way to reach admissions staff.
The FAQ must cover the most common applicant questions (deadlines, costs, requirements, procedures, contacts).
constraints
The FAQ knowledge base must be kept up to date by admissions staff — no outdated answers.
Answers must be available in Kazakh, Russian, and English.
tags
Volatility = Low
test scripts
System: (Pass) Five (5) different FAQ questions are answered correctly and clearly.
System: (Fail) No answer is returned for a question covered in the FAQ.
System: (Fail) An outdated or incorrect FAQ answer is returned.
System: (Deferred) FAQ answer is returned with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured, searchable FAQ knowledge base covering common admission questions.
Task (New): Create a fallback mechanism that flags unanswered questions and routes them to admissions staff.
Task (Verified): Set up a workflow for admissions staff to review and update FAQ entries regularly.

## US5QATest
The Given/When/Then Acceptance Criteria — Story 5 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 5)
User story: Admission FAQ | As an applicant, I want to receive answers to frequently asked questions about admission, so that I don't have to search for information manually on the university website.
Scenario 1 | Successful FAQ query
Given | The user opens the chatbot
When | The user asks a common admission question
Then | The system returns the correct FAQ answer
Scenario 2 | Question not covered in FAQ
Given | The user asks a question not covered in the FAQ
When | The chatbot searches the FAQ knowledge base
Then | The system informs the user the question isn't covered
And | The system offers to connect the user with admissions staff

## User Story 6
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US6QATest)
Application Status Check :As an applicant, I want to check my application status through the assistant, so that I know at which stage my application currently is. | Applicant, Admissions Office
responsibilities
The system must retrieve and display the applicant's current application status in real-time (e.g., submitted, under review, documents required, accepted, rejected).
A user must be warned when the status demonstration is going to be delayed for more than 5 seconds or there is no connection with the database.
The system must authenticate the applicant before showing any status information.
constraints
The solution must use the university's existing application-status database/records.
Status changes must be reflected in near real-time mode.
tags
Volatility = Medium
test scripts
System: (Pass) Five (5) different status requests are successfully retrieved and displayed correctly.
System: (Fail) No status is shown for a valid application.
System: (Fail) An incorrect status is displayed.
System: (Deferred) Status is shown with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create the integration linking the assistant to the application-status database/records.
Task (New): Create the authentication flow to verify the applicant before displaying status.
Task (Verified): Create logging to compare displayed status against the source database for accuracy checks.

## US6QATest
The Given/When/Then Acceptance Criteria — Story 6 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 6)
User story: Application Status Check | As an applicant, I want to check my application status through the assistant, so that I know at which stage my application currently is.
Scenario 1 | Successful status check
Given | The user logs in to the system
When | The user requests their application status
Then | The system shows the current status based on the latest application records
Scenario 2 | System delays with showing status
Given | The user logs in to the system
When | The user requests their application status
Then | The system delays with showing the status for more than 5 seconds
And | The system shows a feedback message asking the user to try again or wait

## User Story 7
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US7QATest)
Admission Procedure Walkthrough :As an applicant, I want to receive a step-by-step guide on the admission procedure, so that I understand what actions I need to take. | Applicant, Admissions Office
responsibilities
The system must present admission steps in the correct sequential order, based on the applicant's chosen program.
The user must be warned if a step requires an action with a deadline (e.g., "submit by [date]").
The guide must update automatically if the university changes its admission procedure.
constraints
The guide must reflect the official, currently approved admission procedure — no outdated steps.
The guide must be accessible both inside the chatbot and as a standalone reference (e.g., linked page).
tags
Volatility = Medium
test scripts
System: (Pass) The full step-by-step sequence is displayed correctly for a given program.
System: (Fail) A step is missing or shown out of order.
System: (Fail) An outdated procedure step is shown.
System: (Deferred) The guide loads with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a data structure representing ordered admission steps per program/applicant type.
Task (New): Build a UI/chat flow that walks the user through each step with clear progress indication.
Task (Verified): Set up a process for admissions staff to update the procedure steps when policy changes.

## US7QATest
The Given/When/Then Acceptance Criteria — Story 7 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 7)
User story:Chat-Program Info | As an applicant, I want to receive a step-by-step guide on the admission procedure, so that I understand what actions I need to take.
Scenario 1 | Scenario 1
Given | The user selects a program of interest
When | The user requests the admission procedure guide
Then | The system displays the correct ordered list of steps for that program
Scenario 2 | Procedure updated
Given | The admission procedure has changed
When | The user requests the guide
Then | The system displays the most recently updated version of the steps

## User Story 8
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US8QATest)
Deadline Information :As an applicant, I want to receive information about document and application submission deadlines, so that I don't miss important dates. | Applicant, Admissions Office
responsibilities
The chatbot must provide accurate, program-specific deadlines for document submission and application stages.
A user must be warned if a requested deadline has already passed or is not yet confirmed.
The system should be able to proactively remind the user of an upcoming deadline if requested.
constraints
Deadline information must reflect the official, currently approved admissions calendar — no outdated dates.
Answers must be available in Kazakh, Russian, and English.
tags
Volatility = Medium
test scripts
System: (Pass) Correct deadlines are returned for five (5) different program/stage combinations.
System: (Fail) No deadline is returned for a valid program/stage.
System: (Fail) An outdated or incorrect deadline is returned.
System: (Deferred) Deadline information is returned with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured database of admission deadlines per program and application stage.
Task (New): Create a reminder mechanism to notify applicants of upcoming deadlines.
Task (Verified): Set up periodic sync between the deadline database and the official admissions calendar.

## US8QATest
The Given/When/Then Acceptance Criteria — Story 8 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 8)
User story: Deadline Information | As an applicant, I want to receive information about document and application submission deadlines, so that I don't miss important dates.
Scenario 1 | Successful deadline query
Given | The user opens the chatbot
When | The user asks about the deadline for a specific program/stage
Then | The system returns the correct, current deadline
Scenario 2 | Deadline already passed
Given | The user asks about a deadline that has already passed
When | The chatbot checks the deadline database
Then | The system informs the user the deadline has passed
And | The system suggests an alternative action (e.g., contact admissions office)

## User Story 9
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US9QATest)
Official Source Links :As an applicant, I want to receive links to the university's official sources, so that I can independently verify important information. | Applicant, Admissions Office
responsibilities
The chatbot must provide a relevant, working link to the official university source when answering questions where verification matters (policies, requirements, deadlines).
A user must be warned if no official source link is available for a given topic.
The chatbot must ensure the provided links point to the current, correct page — not outdated or broken URLs.
constraints
Links must point only to official university domains/pages — no third-party or unofficial sources.
Links must be periodically checked to ensure they are not broken or outdated.
tags
Volatility = Low
test scripts
System: (Pass) A correct, working official link is returned for five (5) different topics.
System: (Fail) No link is returned when an official source exists for the topic.
System: (Fail) A broken or outdated link is returned.
System: (Deferred) The link is returned with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured mapping of topics to official university source URLs.
Task (New): Create a fallback message for topics without an available official source link.
Task (Verified): Set up periodic link-checking to detect and flag broken or outdated URLs.

## US9QATest
The Given/When/Then Acceptance Criteria — Story 9 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 9)
User story: Official Source Links | As an applicant, I want to receive links to the university's official sources, so that I can independently verify important information.
Scenario 1 | Successful link retrieval
Given | The user opens the chatbot
When | The user asks for an official source on a specific topic
Then | The system returns a correct, working link to the official page
Scenario 2 | No official source available
Given | The user asks for an official source on a topic without a mapped link
When | The chatbot searches the source mapping
Then | The system informs the user no official link is currently available
And | The system offers to connect the user with admissions staff

## User Story 10
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US10QATest)
Update Admission Info :As a university staff member, I want to update the admission information used by the assistant, so that applicants receive up-to-date data. | University Staff, Admissions Office
responsibilities
The system must allow authorized staff to add, edit, or remove admission information (programs, requirements, deadlines, documents) used by the assistant.
The system must validate updates before publishing them, so incorrect or incomplete data is not shown to applicants.
The assistant must reflect approved updates without requiring a full system redeployment.
constraints
Only authorized staff (verified role/permissions) may modify admission information.
All updates must be logged, including who made the change and when.
tags
Volatility = Medium
test scripts
System: (Pass) An authorized staff member successfully updates information, and the assistant reflects the change correctly in five (5) test cases.
System: (Fail) An unauthorized user is able to modify admission information.
System: (Fail) An update is published without required fields, resulting in incomplete data shown to applicants.
System: (Deferred) An approved update takes longer than the acceptable threshold to appear in the assistant.
maintenance
Task (New): Create a staff-facing interface/panel for managing admission information.
Task (New): Create a role-based access control mechanism restricting edits to authorized staff.
Task (Verified): Create an audit log tracking all changes with author and timestamp.

## US10QATest
The Given/When/Then Acceptance Criteria — Story 10 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 10)
User story: Update Admission Info | As a university staff member, I want to update the admission information used by the assistant, so that applicants receive up-to-date data.
Scenario 1 | Successful information update
Given | The staff member is logged in with authorized permissions
When | The staff member submits a valid update to admission information
Then | The system publishes the update and the assistant reflects it correctly
Scenario 2 | Unauthorized update attempt
Given | The user does not have authorized staff permissions
When | The user attempts to modify admission information
Then | The system rejects the update
And | The system logs the unauthorized attempt

## User Story 11
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US11QATest)
Multilingual Support :As an applicant, I want to interact with the assistant in Kazakh, Russian, or English, so that I can receive information in the language I'm most comfortable with. | Applicant, Admissions Office
responsibilities
The assistant must detect or let the user select their preferred language and respond consistently in that language throughout the conversation.
A user must be warned if a requested language is not yet supported for a specific piece of content.
The assistant must maintain consistent terminology and accuracy across all three supported languages.
constraints
The assistant must support Kazakh, Russian, and English for all core functions (chatbot queries, FAQ, status check, document guidance).
Translated content must be reviewed for accuracy — no unreviewed machine-translation-only content for critical information (deadlines, requirements).
tags
Volatility = Low
test scripts
System: (Pass) The assistant correctly responds in the selected language for five (5) different queries across all three languages.
System: (Fail) The assistant responds in the wrong language after a language has been selected.
System: (Fail) Content is missing or untranslated in a supported language.
System: (Deferred) Language switch takes longer than the acceptable threshold to apply.
maintenance
Task (New): Create a language-selection mechanism (manual selection and/or auto-detection).
Task (New): Create and maintain translated content for all core assistant functions in Kazakh, Russian, and English.
Task (Verified): Set up a review process to verify translation accuracy for critical information.

## US11QATest
The Given/When/Then Acceptance Criteria — Story 11 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 11)
User story: Multilingual Support | As an applicant, I want to interact with the assistant in Kazakh, Russian, or English, so that I can receive information in the language I'm most comfortable with.
Scenario 1 | Successful language interaction
Given | The user selects their preferred language (Kazakh, Russian, or English)
When | The user asks a question in the chatbot
Then | The system responds accurately in the selected language
Scenario 2 | Unsupported content in selected language
Given | The user has selected a supported language
When | The requested content is not yet available in that language
Then | The system informs the user the content isn't available in that language
And | The system offers the content in an available language as a fallback

## User Story 12
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US12QATest)
Program Comparison :As an applicant, I want to compare several programs by criteria (cost, grants, passing score), so that I can make an informed decision. | Applicant, Admissions Office
responsibilities
The assistant must allow the applicant to select two or more programs and display their key criteria side by side (cost, available grants, passing score, duration).
A user must be warned if comparison data for a selected program is incomplete or unavailable.
The comparison must be presented in a clear, easy-to-read format.
constraints
Comparison data must reflect the official, currently approved program information — no outdated figures.
The assistant must support comparing at least 2 and up to 4 programs at once.
tags
Volatility = Medium
test scripts
System: (Pass) A correct side-by-side comparison is generated for five (5) different program combinations.
System: (Fail) The comparison is missing a criterion for one of the selected programs.
System: (Fail) Outdated or incorrect comparison data is displayed.
System: (Deferred) The comparison is generated with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a structured dataset of comparable criteria (cost, grants, passing score, duration) per program.
Task (New): Build a side-by-side comparison view/response format for the assistant.
Task (Verified): Set up periodic sync between the comparison dataset and the official program data source.

## US12QATest
The Given/When/Then Acceptance Criteria — Story 12 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 12)
User story: Program Comparison | As an applicant, I want to compare several programs by criteria (cost, grants, passing score), so that I can make an informed decision.
Scenario 1 | Successful comparison
Given | The user selects two or more programs to compare
When | The user requests a comparison
Then | The system displays a correct side-by-side comparison of the selected programs
Scenario 2 | Incomplete comparison data
Given | The user selects a program with missing comparison data
When | The user requests a comparison
Then | The system warns the user that data is incomplete for that program
And | The system displays the available criteria for the remaining programs

## User Story 13
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US13QATest)
Manage FAQ Database :As a university staff member, I want to manage the FAQ knowledge base, so that the chatbot provides accurate answers to common applicant questions. | University Staff, Admissions Office
responsibilities
The system must allow authorized staff to add, edit, or remove FAQ entries used by the assistant.
The system must validate new/edited FAQ entries before publishing, so incomplete or unclear answers are not shown to applicants.
The assistant must reflect approved FAQ changes without requiring a full system redeployment.
constraints
Only authorized staff (verified role/permissions) may modify the FAQ database.
All FAQ changes must be logged, including who made the change and when.
tags
Volatility = Low
test scripts
System: (Pass) An authorized staff member successfully adds/edits an FAQ entry, and the assistant reflects the change correctly in five (5) test cases.
System: (Fail) An unauthorized user is able to modify the FAQ database.
System: (Fail) An FAQ entry is published without required fields, resulting in an incomplete answer shown to applicants.
System: (Deferred) An approved FAQ change takes longer than the acceptable threshold to appear in the assistant.
maintenance
Task (New): Create a staff-facing interface/panel for managing FAQ entries.
Task (New): Create a role-based access control mechanism restricting FAQ edits to authorized staff.
Task (Verified): Create an audit log tracking all FAQ changes with author and timestamp.

## US13QATest
The Given/When/Then Acceptance Criteria — Story 13 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 13)
User story: Manage FAQ Database | As a university staff member, I want to manage the FAQ knowledge base, so that the chatbot provides accurate answers to common applicant questions.
Scenario 1 | Successful FAQ update
Given | The staff member is logged in with authorized permissions
When | The staff member adds or edits an FAQ entry
Then | The system publishes the entry and the assistant reflects it correctly
Scenario 2 | Unauthorized FAQ modification attempt
Given | The user does not have authorized staff permissions
When | The user attempts to modify the FAQ database
Then | The system rejects the change
And | The system logs the unauthorized attempt

## User Story 14
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US14QATest)
Escalation Notification :As an applicant, I want to be notified when the assistant cannot confidently answer my question, so that I can contact the appropriate university department. | Applicant, Admissions Office
responsibilities
The assistant must detect when it cannot confidently answer a question and notify the applicant clearly, rather than guessing.
The notification must direct the applicant to the correct department/contact relevant to their question.
A user must be warned if the escalation itself fails (e.g., no contact route available), so they are not left without any next step.
constraints
The confidence threshold for triggering escalation must be configurable by staff, not hardcoded.
Escalation routing must map to the correct department based on question topic (admissions, financial aid, technical support, etc.).
tags
Volatility = Medium
test scripts
System: (Pass) Escalation notification with correct department routing is triggered for five (5) different low-confidence questions.
System: (Fail) A low-confidence question is answered without triggering escalation.
System: (Fail) Escalation routes to the wrong department.
System: (Deferred) Escalation notification is shown with a delay exceeding the acceptable threshold.
maintenance
Task (New): Create a confidence-scoring mechanism to detect when the assistant should escalate rather than answer.
Task (New): Create a topic-to-department routing map for escalation.
Task (Verified): Set up a configuration panel for staff to adjust the confidence threshold.

## US14QATest
The Given/When/Then Acceptance Criteria — Story 14 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 14)
User story: Escalation Notification | As an applicant, I want to be notified when the assistant cannot confidently answer my question, so that I can contact the appropriate university department.
Scenario 1 | Successful escalation
Given | The user asks a question the assistant cannot confidently answer
When | The confidence score falls below the threshold
Then | The system notifies the user and directs them to the correct department
Scenario 2 | No escalation route available
Given | The assistant cannot confidently answer and no matching department route exists
When | The escalation is triggered
Then | The system informs the user no specific route is available
And | The system provides a general admissions contact as a fallback

## User Story 15
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US15QATest)
Account Registration & Verification :As an applicant, I want to register an account using my email or phone number and verify it via a 6-digit code (Email, SMS, or Telegram Bot), so that my data is securely stored and authenticated. | Applicant, Admissions Office
responsibilities
The system must allow registration using email or phone number with secure password hashing.
The system must generate a 6-digit verification code and deliver it via the chosen channel (Email, SMS, or Telegram Bot deep-link).
The system must activate the account only after successful verification of the 6-digit code within its 15-minute expiration window.
constraints
Phone numbers and email addresses must be unique per verified account.
Passwords must meet minimum security requirements (at least 8 characters, letters, and numbers).
tags
Volatility = Low
test scripts
System: (Pass) User successfully registers via Email/Telegram/SMS and activates their account with the correct code.
System: (Fail) Verification code expired or invalid code entered 3 times.
System: (Fail) Registration attempted with an already registered and verified email or phone.
System: (Deferred) SMS delivery delayed beyond 60 seconds due to carrier network congestion.
maintenance
Task (New): Implement AccountVerificationToken model and delivery dispatchers for Email, SMS, and Telegram bot.
Task (Verified): Validate expiration and single-use invalidation of verification tokens.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US15QATest
The Given/When/Then Acceptance Criteria - Story 15 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 15)
User story: Account Registration & Verification | As an applicant, I want to register an account using my email or phone number and verify it via a 6-digit code (Email, SMS, or Telegram Bot), so that my data is securely stored and authenticated.
Scenario 1 | Successful multi-channel registration and verification
Given | The user navigates to the registration form
When | The user enters valid credentials and selects Email or Phone verification
Then | The system issues a 6-digit code and activates the account upon correct submission
Scenario 2 | Invalid or expired verification code
Given | An unverified user receives a verification code
When | The user enters an incorrect code or attempts submission after 15 minutes
Then | The system rejects activation and provides an option to resend a new code
And | The user can request a fresh code via the resend endpoint

## User Story 16
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US16QATest)
Applicant Profile & Saved Programs :As an applicant, I want to create a personal profile with my target degree and bookmark preferred programs, so that I can easily track my favorite educational choices. | Applicant, Admissions Office
responsibilities
The system must allow applicants to set citizenship (domestic/international) and target degree (undergraduate/graduate) in their profile.
The system must allow users to bookmark/save programs from the catalog and view their saved list in their profile.
The system must allow users to remove programs from their saved list at any time.
constraints
Only authenticated applicants can access personal profiles and save programs.
Saved programs must link directly to official catalog entries.
tags
Volatility = Low
test scripts
System: (Pass) User bookmarks three programs and views them correctly listed in their profile dashboard.
System: (Fail) Duplicate bookmarking of the same program causes redundant entries.
System: (Fail) Unauthenticated guest tries to access profile data without logging in.
System: (Deferred) Profile update takes longer than 2 seconds under peak database load.
maintenance
Task (New): Create ApplicantProfile and SavedProgram database models with foreign keys to User and Program.
Task (Verified): Add REST endpoints /auth/me, /applicant/profile, and /applicant/saved-programs.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US16QATest
The Given/When/Then Acceptance Criteria - Story 16 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 16)
User story: Applicant Profile & Saved Programs | As an applicant, I want to create a personal profile with my target degree and bookmark preferred programs, so that I can easily track my favorite educational choices.
Scenario 1 | Bookmarking a program
Given | An authenticated applicant is viewing program details
When | The applicant clicks the 'Save Program' bookmark button
Then | The program is saved to the applicant's profile and displayed in their wishlist
Scenario 2 | Removing a saved program
Given | An applicant has programs in their saved list
When | The applicant clicks 'Remove' on a saved program
Then | The program is removed from the saved list immediately
And | The applicant's wishlist count updates in real time

## User Story 17
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US17QATest)
Secure Password Recovery :As an applicant, I want to reset my password using a secure 6-digit code delivered via email or Telegram bot, so that I can regain access if I forget my password. | Applicant, Admissions Office
responsibilities
The system must allow users to request password recovery by entering their registered email.
The system must offer delivery of the reset code via Email or via Telegram bot deep linking.
The system must allow setting a new password only after validating the 6-digit code.
constraints
Password reset tokens must expire after 15 minutes and become invalid immediately upon use.
Previous tokens must be automatically invalidated when a new reset request is made.
tags
Volatility = Low
test scripts
System: (Pass) User receives a reset code via Telegram or Email, sets a new password, and logs in successfully.
System: (Fail) User attempts to reset password with an expired or previously used code.
System: (Fail) Request submitted for an unregistered email address.
System: (Deferred) Email delivery exceeds 3 minutes due to external mail relay.
maintenance
Task (New): Implement PasswordResetToken model with Telegram bot webhook integration.
Task (Verified): Ensure passwords are encrypted with bcrypt upon update.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US17QATest
The Given/When/Then Acceptance Criteria - Story 17 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 17)
User story: Secure Password Recovery | As an applicant, I want to reset my password using a secure 6-digit code delivered via email or Telegram bot, so that I can regain access if I forget my password.
Scenario 1 | Password reset via Telegram Bot
Given | An applicant forgot their account password
When | The applicant selects Telegram reset and sends /start reset_<CODE> to the bot
Then | The bot delivers the 6-digit code, and the website allows entering the new password
Scenario 2 | Expired reset code attempt
Given | An applicant requested a reset code over 15 minutes ago
When | The applicant attempts to submit the new password with the old code
Then | The system rejects the request and prompts the user to request a fresh code
And | The previous code remains unusable in the database

## User Story 18
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US18QATest)
UNT Eligibility Matcher :As an applicant, I want to enter my UNT profile subjects and scores, so that the assistant can instantly show which programs I am qualified to apply for. | Applicant, Admissions Office
responsibilities
The system must accept the applicant's two specialized UNT subjects and total score (out of 140).
The system must match the entered profile against university admission thresholds (minimum 50/65/75 points depending on program).
The system must display a filtered list of eligible programs with required vs achieved score comparison.
constraints
Must comply with official Ministry of Science and Higher Education UNT passing score rules.
Must validate that the subject combination matches the Kazakh national classifier.
tags
Volatility = Medium
test scripts
System: (Pass) Correct list of eligible programs returned for 'Math + Physics' with score 95.
System: (Fail) Applicant with score below the minimum threshold (e.g. 45) is incorrectly marked eligible.
System: (Fail) Invalid subject combination entered (e.g. identical subjects).
System: (Deferred) Complex multi-faculty eligibility query response time > 1.5 seconds.
maintenance
Task (New): Create UNT score validation and program matching engine in backend.
Task (Verified): Validate matching against 2026 official SDU admission minimums.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US18QATest
The Given/When/Then Acceptance Criteria - Story 18 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 18)
User story: UNT Eligibility Matcher | As an applicant, I want to enter my UNT profile subjects and scores, so that the assistant can instantly show which programs I am qualified to apply for.
Scenario 1 | Matching eligible programs
Given | The applicant enters UNT subjects 'Math + Computer Science' and score 100
When | The applicant requests matching programs
Then | The system returns all IT programs where the score meets or exceeds the minimum cutoff
Scenario 2 | Score below threshold
Given | The applicant enters a score below the program minimum requirement
When | The applicant checks eligibility for that specific program
Then | The system clearly indicates the score deficit and suggests foundation or alternative programs
And | The assistant offers advice on retake opportunities

## User Story 19
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US19QATest)
Tuition & Grant Calculator :As an applicant, I want to calculate estimated annual tuition fees and my probability of winning a state or university grant, so that I can plan my higher education budget. | Applicant, Admissions Office
responsibilities
The system must calculate annual and 4-year tuition fees based on chosen program and payment format.
The system must evaluate grant probability (High, Medium, Low) based on historical grant cutoff scores.
The system must show applicable internal university discounts (Altyn Belgi, olympiad winners, social discounts).
constraints
Must explicitly state that grant probability estimates are advisory and subject to official competition.
Must support calculations in Kazakh Tenge (KZT) with updated 2026-2027 academic year rates.
tags
Volatility = Medium
test scripts
System: (Pass) Accurate tuition calculation and grant probability returned for high UNT score (120+).
System: (Fail) Calculation fails or shows negative fee when discount is applied.
System: (Fail) Outdated tuition rates from previous academic year are used.
System: (Deferred) Calculator currency formatting error on localized view.
maintenance
Task (New): Build tuition calculation and historical grant cutoff model.
Task (Verified): Verify tuition discount rules against SDU financial aid policy.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US19QATest
The Given/When/Then Acceptance Criteria - Story 19 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 19)
User story: Tuition & Grant Calculator | As an applicant, I want to calculate estimated annual tuition fees and my probability of winning a state or university grant, so that I can plan my higher education budget.
Scenario 1 | Estimating grant probability
Given | The applicant enters a high UNT score (e.g. 125 in IT)
When | The applicant runs the grant calculator
Then | The system indicates 'High Probability' for state grant and displays historical cutoffs
Scenario 2 | Internal university discount calculation
Given | The applicant selects 'Olympiad Winner' discount category
When | The applicant calculates tuition fees
Then | The system computes the discounted annual fee and payment installment breakdown
And | The system displays the necessary documentation required to claim the discount

## User Story 20
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US20QATest)
Telegram Push Alerts :As an applicant, I want to receive automated push alerts in Telegram 3 days and 1 day before application deadlines, so that I never miss submission cutoffs. | Applicant, Admissions Office
responsibilities
The system must track key admission campaign milestones (UNT registration, grant application, document submission).
The system must dispatch scheduled Telegram push notifications to opted-in applicants before impending deadlines.
The system must provide a one-click Telegram button to view checklist steps required for the approaching deadline.
constraints
Alerts must only be sent to applicants with verified telegram_chat_id.
Notification sending must respect timezones (Almaty time, UTC+5) and not message during night hours.
tags
Volatility = Low
test scripts
System: (Pass) Automated reminder dispatched exactly 72 hours before grant competition closing date.
System: (Fail) Duplicate reminder sent multiple times to the same chat.
System: (Fail) Notification sent to an unlinked or deactivated Telegram user.
System: (Deferred) High-volume reminder batch queue delayed by more than 15 minutes.
maintenance
Task (New): Create cron/scheduler task for deadline reminders linked to Telegram service.
Task (Verified): Implement notification opt-in/opt-out toggle in user profile.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US20QATest
The Given/When/Then Acceptance Criteria - Story 20 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 20)
User story: Telegram Push Alerts | As an applicant, I want to receive automated push alerts in Telegram 3 days and 1 day before application deadlines, so that I never miss submission cutoffs.
Scenario 1 | Scheduled deadline alert
Given | An applicant linked their Telegram bot account and an admission deadline is 3 days away
When | The daily scheduler runs the reminder job
Then | The applicant receives a formatted reminder with deadline date and action link
Scenario 2 | Muted notifications
Given | An applicant turned off reminder notifications in their profile
When | The reminder job executes
Then | The system skips that user without sending Telegram messages
And | The user's preference state is preserved accurately

## User Story 21
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US21QATest)
Document Pre-check Validator :As an applicant, I want to check my document readiness against a real-time checklist and upload test scans to verify format compliance (PDF/JPEG), so that my application is not rejected. | Applicant, Admissions Office
responsibilities
The system must display an interactive document readiness checklist tailored to applicant status (local/foreign).
The system must allow uploading sample files and validate file extensions (.pdf, .jpg, .png) and max file sizes (up to 10MB).
The system must show a readiness progress bar (e.g. 4/6 documents ready).
constraints
Uploaded files must be scanned for security and stored securely without public exposure.
Verification status must clearly differentiate between 'User Uploaded' and 'Staff Verified'.
tags
Volatility = Medium
test scripts
System: (Pass) User uploads valid PDF certificate; file size verified and marked 'Ready' on checklist.
System: (Fail) Upload of unsupported file format (e.g. .exe or .zip) is accepted.
System: (Fail) File exceeding 10MB limit crashes upload handler without error message.
System: (Deferred) Virus scan latency exceeds 5 seconds per file upload.
maintenance
Task (New): Implement file validation utility and document checklist UI component.
Task (Verified): Ensure strict MIME-type validation and storage isolation.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US21QATest
The Given/When/Then Acceptance Criteria - Story 21 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 21)
User story: Document Pre-check Validator | As an applicant, I want to check my document readiness against a real-time checklist and upload test scans to verify format compliance (PDF/JPEG), so that my application is not rejected.
Scenario 1 | Uploading valid document scan
Given | The applicant views their required documents checklist
When | The applicant uploads an ID card scan in PDF format (3 MB)
Then | The system validates file format and updates checklist progress to 'Ready'
Scenario 2 | Unsupported file format
Given | The applicant attempts to upload an unsupported format (.docx)
When | The upload is submitted
Then | The system displays a validation error detailing allowed formats (.pdf, .jpeg, .png)
And | The file is discarded without being stored

## User Story 22
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US22QATest)
Online Application Submission :As an applicant, I want to submit a preliminary admission application with my contact details and chosen specialty online, so that the university admissions committee can review it immediately. | Applicant, Admissions Office
responsibilities
The system must guide applicants through a 3-step application form: personal data, program selection, and document attachments.
The system must generate a unique Application Reference Number (e.g. APP-2026-XXXX).
The system must send a confirmation message with application reference number via Email and Telegram.
constraints
Applicant must be verified before submitting an official application.
Each applicant can have only one active preliminary application per academic period.
tags
Volatility = Medium
test scripts
System: (Pass) Application submitted successfully; reference number generated and status set to 'Under Review'.
System: (Fail) Mandatory fields missing but form submits without error.
System: (Fail) User submits multiple duplicate applications simultaneously.
System: (Deferred) Confirmation email delivery delayed by external queue.
maintenance
Task (New): Create Application model with status enum (Draft, Submitted, Under Review, Approved, Rejected).
Task (Verified): Link applications to applicant profile and manager portal.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US22QATest
The Given/When/Then Acceptance Criteria - Story 22 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 22)
User story: Online Application Submission | As an applicant, I want to submit a preliminary admission application with my contact details and chosen specialty online, so that the university admissions committee can review it immediately.
Scenario 1 | Successful application submission
Given | A verified applicant filled in all required application fields
When | The applicant clicks 'Submit Application'
Then | The application is saved, a unique reference number is assigned, and confirmation is sent
Scenario 2 | Submission with incomplete data
Given | An applicant missed mandatory contact information
When | The applicant attempts submission
Then | The system highlights missing fields and blocks submission until corrected
And | Form inputs remain saved as draft

## User Story 23
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US23QATest)
Staff Application Review Portal :As an admissions manager, I want to view incoming applications, change review statuses (Pending, Approved, Requires Correction), and add staff comments, so that applicants are kept informed. | University Staff, Admissions Office
responsibilities
The system must provide a secure manager view of all submitted applications with search and status filters.
The manager must be able to change application status (Pending, Approved, Needs Correction, Rejected).
The manager must be able to leave internal review notes and feedback visible to the applicant.
constraints
Only users with role manager or admin can access the review dashboard.
Every status change must record audit timestamp and manager ID.
tags
Volatility = Medium
test scripts
System: (Pass) Manager updates application status to 'Needs Correction' with note; applicant sees updated status immediately.
System: (Fail) Non-staff applicant accesses staff review endpoint.
System: (Fail) Status update succeeds without recording manager audit log.
System: (Deferred) Loading 500+ application records in manager grid takes > 3 seconds.
maintenance
Task (New): Add SQLAdmin view and REST endpoints for application status review.
Task (Verified): Enforce RBAC permission checks on all manager endpoints.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US23QATest
The Given/When/Then Acceptance Criteria - Story 23 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 23)
User story: Staff Application Review Portal | As an admissions manager, I want to view incoming applications, change review statuses (Pending, Approved, Requires Correction), and add staff comments, so that applicants are kept informed.
Scenario 1 | Approving applicant documents
Given | An admissions manager opens an application with complete documents
When | The manager sets status to 'Approved' and enters an approval comment
Then | The status is updated in the database and the applicant receives notification
Scenario 2 | Requesting document corrections
Given | An application contains an illegible document scan
When | The manager sets status to 'Needs Correction' with instructions
Then | The applicant portal prompts for re-uploading the specific document
And | The applicant receives an email alert with the manager's remarks

## User Story 24
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US24QATest)
Career Pathways Advisor :As an applicant, I want to see typical career roles, average starting salaries, and partner hiring companies for each program, so that I can choose a major with clear career prospects. | Applicant, Admissions Office
responsibilities
The system must display career prospects and top employment sectors for each academic specialty.
The chatbot must answer career-oriented questions (e.g. 'Where can I work after graduating Software Engineering?').
The system must list university partner organizations and internship opportunities for each faculty.
constraints
Salary and employment rates must cite verifiable university alumni statistics.
Data must be available in Kazakh, Russian, and English.
tags
Volatility = Low
test scripts
System: (Pass) Chatbot correctly answers career and salary inquiry for 'Information Systems'.
System: (Fail) Question about program careers returns generic template without specific roles.
System: (Fail) Outdated partner company list shown.
System: (Deferred) Multi-language career data rendering latency.
maintenance
Task (New): Enrich program database schema with career_paths, avg_salary, and partner_employers.
Task (Verified): Update chatbot prompt to leverage career data in recommendation responses.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US24QATest
The Given/When/Then Acceptance Criteria - Story 24 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 24)
User story: Career Pathways Advisor | As an applicant, I want to see typical career roles, average starting salaries, and partner hiring companies for each program, so that I can choose a major with clear career prospects.
Scenario 1 | Asking chatbot about career opportunities
Given | An applicant asks 'What career options exist for Computer Science graduates?'
When | The chatbot searches the program knowledge base
Then | The system returns specific job titles, top hiring partners, and employment rate
Scenario 2 | Viewing career tab on program detail
Given | An applicant views the program overview page
When | The applicant navigates to 'Career & Internships' section
Then | The system displays verified alumni employment statistics and partner companies
And | Links to alumni success stories are provided

## User Story 25
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US25QATest)
Excel Report Export for Admissions :As an admissions manager, I want to export applicant registrations, inquiries, and popular program statistics into Excel spreadsheets (.xlsx), so that the admissions department can prepare official recruitment reports. | University Staff, Admissions Office
responsibilities
The system must generate formatted Excel (.xlsx) reports of registered applicants and verification statuses.
The system must export aggregate program interest analytics (total bookmarks, inquiries, popular faculties).
The system must allow date range filtering for exported reports (daily, weekly, whole campaign).
constraints
Personal applicant data export must be restricted to authorized admissions managers.
Generated Excel files must include column headers, timestamps, and data types formatted cleanly.
tags
Volatility = Low
test scripts
System: (Pass) Manager exports 100+ applicant records to valid .xlsx workbook with proper columns.
System: (Fail) Unauthorized user attempts to download export endpoint without manager credentials.
System: (Fail) Exported Excel file is corrupted or contains empty sheets.
System: (Deferred) Generating large Excel file (10,000+ rows) takes more than 10 seconds.
maintenance
Task (New): Implement openpyxl export services in app/excel_service.py with FastAPI streaming response.
Task (Verified): Add 'Export to Excel' action buttons to SQLAdmin dashboard.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US25QATest
The Given/When/Then Acceptance Criteria - Story 25 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 25)
User story: Excel Report Export for Admissions | As an admissions manager, I want to export applicant registrations, inquiries, and popular program statistics into Excel spreadsheets (.xlsx), so that the admissions department can prepare official recruitment reports.
Scenario 1 | Exporting applicant list to Excel
Given | An admissions manager is in the admin reporting section
When | The manager clicks 'Export Applicants to Excel'
Then | The browser downloads a valid .xlsx file containing applicant names, contacts, and status
Scenario 2 | Program popularity export
Given | A manager selects date range for the current sprint
When | The manager requests program analytics export
Then | The system generates a formatted spreadsheet summarizing inquiry counts per specialty
And | Aggregate summary statistics are appended at the bottom

## User Story 26
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US26QATest)
Live Admissions Officer Chat Handoff :As an applicant, when the automated assistant cannot answer my complex personal question, I want to be transferred to a live admissions officer, so that I can receive real-time human assistance. | Applicant, Admissions Office
responsibilities
The system must provide a seamless handoff button when confidence score is low or when user requests human operator.
The system must queue the chat session in the manager dashboard and notify available officers.
The admissions officer must be able to join the conversation and send messages directly to the applicant's chat widget.
constraints
When no human operators are online, the system must clearly notify the user and collect contact info for callback.
Chat history must be preserved so the operator understands context without repeating questions.
tags
Volatility = High
test scripts
System: (Pass) User clicks 'Connect to Officer'; session status updates to 'escalated'; officer sends response received in real time.
System: (Fail) Operator message fails to deliver to user chat session.
System: (Fail) Multiple operators accept the same session concurrently causing collision.
System: (Deferred) WebSocket connection reconnect delay exceeding 5 seconds.
maintenance
Task (New): Add live operator routing, chat session status transitions, and operator chat interface.
Task (Verified): Ensure seamless handoff transition from AI bot to human operator.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US26QATest
The Given/When/Then Acceptance Criteria - Story 26 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 26)
User story: Live Admissions Officer Chat Handoff | As an applicant, when the automated assistant cannot answer my complex personal question, I want to be transferred to a live admissions officer, so that I can receive real-time human assistance.
Scenario 1 | Successful live operator escalation
Given | An applicant asks a complex question about a specialized document concession
When | The applicant selects 'Speak with Officer'
Then | The session is placed in the escalation queue, an officer joins, and live chat is established
Scenario 2 | Offline operator fallback
Given | No admissions officers are online after operating hours
When | An applicant requests human escalation
Then | The system informs the user and records a callback inquiry with applicant contact info
And | The chat history is saved for offline follow-up

## User Story 27
User Story | Stakeholders: | ⬅️ Back to Main Schedule | ➡️ View QA Test (US27QATest)
Assistant Feedback & Quality Rating :As an applicant, I want to submit a 1-to-5 star rating and optional comments on the assistant's answer quality, so that the university can monitor satisfaction and improve the chatbot. | Applicant, Admissions Office
responsibilities
The system must present a lightweight satisfaction rating widget (1-5 stars or thumbs up/down) at the end of chat sessions.
The system must allow submitting optional text feedback explaining the rating.
The system must aggregate feedback metrics (average CSAT score, low-rating transcripts) in the admin dashboard.
constraints
Rating must be optional and non-intrusive.
Each chat session can submit only one rating to prevent score manipulation.
tags
Volatility = Low
test scripts
System: (Pass) User rates chat 5 stars with comment; feedback saved and linked to session ID.
System: (Fail) Feedback submission crashes when user submits rating without text comments.
System: (Fail) Same user submits multiple conflicting ratings on one session.
System: (Deferred) Feedback analytics chart rendering time.
maintenance
Task (New): Implement Feedback database model and API endpoints POST /feedback and GET /admin/feedback.
Task (Verified): Add average rating score widget to admin statistics view.
Task (Verified): Set up periodic sync between the chatbot's document checklist and the official admissions policy source.

## US27QATest
The Given/When/Then Acceptance Criteria - Story 27 |  | ⬅️ Back to Main Schedule | 📄 View User Story (User Story 27)
User story: Assistant Feedback & Quality Rating | As an applicant, I want to submit a 1-to-5 star rating and optional comments on the assistant's answer quality, so that the university can monitor satisfaction and improve the chatbot.
Scenario 1 | Submitting positive consultation rating
Given | An applicant received helpful admission answers from the assistant
When | The applicant selects 5 stars and clicks submit
Then | The rating is saved and a thank-you confirmation is displayed
Scenario 2 | Submitting feedback with improvement notes
Given | An applicant was dissatisfied with an incomplete answer
When | The applicant rates 2 stars and enters an explanatory comment
Then | The feedback is flagged for admissions team review and tagged to the conversation transcript
And | Low scores trigger automated alerts in the manager dashboard